## Sheet1
Team B Project Plan
TASK FOCUS |  | TASK LETTER | TASK DESCRIPTION | DATE START | DATE END | PREDECESSOR TASK(s) | RESOURCE(s)
Database
|  | A | Finalize database design (auto-numbered IDs, add tables the app needs) | 2026-10-12 | 2026-10-23 |  | Carlos
|  | B | Create stored procedures (add, edit, delete, look up records) | 2026-10-26 | 2026-11-06 | A | Carlos
|  | C | Populate look up tables and demo data | 2026-10-26 | 2026-11-03 | A | Carlos, Rob
|  | D | Host the database online and set up secure connection | 2026-11-02 | 2026-11-06 | A | Tony, Carlos
Software Development
|  | E | Set up back-end API project | 2026-10-12 | 2026-10-23 |  | Tony
|  | F | Create account API (sign up, sign in, sign out) | 2026-10-26 | 2026-11-06 | A, E | Tony
|  | G | Polish Dashboard, Lab Results and Trends pages | 2026-10-19 | 2026-11-13 |  | Jared
|  | H | Polish Goals, Health History, Documents and Profile pages | 2026-10-19 | 2026-11-13 |  | Rob
|  | I | Create lab results and trends API | 2026-11-09 | 2026-11-20 | B, D, F | Tony
|  | J | Create goals, history and documents API | 2026-11-09 | 2026-11-20 | B, D, F | Carlos
|  | K | Connect the app to the API (replace browser storage) | 2026-11-23 | 2026-12-01 | I, J | Tony, Carlos
|  | L | Deploy app and API online | 2026-12-01 | 2026-12-02 | K | Tony
Unit Test
|  | M | Test account API and login pages | 2026-11-09 | 2026-11-13 | F | Jared
|  | N | Test polished pages (swap: Jared tests Rob's, Rob tests Jared's) | 2026-11-16 | 2026-11-20 | G, H | Jared, Rob
|  | O | Test lab results and trends API | 2026-11-23 | 2026-11-25 | I | Rob
|  | P | Test goals, history and documents API | 2026-11-23 | 2026-11-25 | J | Jared
Integration Test
|  | Q | Develop Testing Plan | 2026-11-16 | 2026-11-20 | C | Rob, Carlos
|  | R | Test Whole Application | 2026-12-02 | 2026-12-04 | Q, K, L, M, N, O, P | Tony, Jared, Rob, Carlos
User Test
|  | S | Develop Test Plan | 2026-11-23 | 2026-11-25 | Q | Jared, Rob
|  | T | Conduct User Test with users | 2026-12-04 | 2026-12-07 | S, R | Team and Users
|  | U | Fix issues found in testing | 2026-12-07 | 2026-12-08 | T | Tony, Carlos
Presentation Development
|  | V | Develop Presentation | 2026-12-01 | 2026-12-07 |  | Team
|  | W | Practice Presentation | 2026-12-08 | 2026-12-09 | V, U | Team
Present Project
|  | X | Present Project | 2026-12-10 | 2026-12-10 | W | Team

## Notes
Assumptions behind this plan (edit as needed)
Work starts Mon Oct 12, 2026; final presentation Thu Dec 10, 2026.
The app connects to the SQL Server database through a back-end API before the presentation.
Database owner: Carlos. Back end and integration: Tony and Carlos. Jared and Rob: page polish, testing, test plans.
The web app front end is already built; Software Development tasks cover the back end, connecting the app, and polishing pages.
Back-end language (e.g. Java Spring Boot) and database host (e.g. Azure SQL) are still to be decided; see task D and E.
Thanksgiving week (Nov 23-27) has lighter tasks; task K runs across it.
Predecessor letters were checked: no task starts before the tasks it depends on finish.